## Sheet1
Description | Evaluation | Likelihood | Impact Level | Responsibility | Response | Control Measures | Updates
Laptop Faliure. | Not able to finish project for client | Low | High | Sean Kaila | Continue development on my own laptop until a replacement arrives | Make sure laptop is update and working correctly regulary | No updates at of 23/04/2021.
Critial information pushed to github. | Results in exposure of passwords and other information to individuals who should not be able to see it | low | high | Sean Kaila | if the information where to reach the wrong had, change the passwords and other informationassociated with data breach | Use a GitIgnore file to hide connection strings, passwords and test result files from being pushed to github | No updates as of 08/05/2021
code Loss (Local) | Key progress of project lost. Therefore not able to deliver project deliverables | low | low | Sean Kaila | Pull latest changes from the branch you're currently working on. | Make sure to regulary push and commit to git | No updates as of 08/05/2021
Azure App Service Outage. | Client will not have access to the production environment. | low | High | Sean Kaila | Deploy project on a parallel app service until the problem is resolved. | Regularly check server status and set up a notification services to let somone know when the service has stopped working. | No updates as of 08/05/2021
MySQL Database Faliure | Loss of core data stops clients from using app. | Low | Meduim | Sean Kaila | Restore database from a backup databse, so that clients go use app once again with minimal loss. | Continue to back up Database twice a day (Every 12 hours.) | No updates as of 08/05/2021
Edit feature failing | Users not being able to use cure functionality. | Medium | High | Sean Kaila | Investigate the issue as soon as it arrives and deploy a hot fix. | Continue to Test edit functionality making sure that its being tested correctly. | No updates as of 08/05/2021
Scope Creep | Results in core areas being unpolished due to the amunt of taks needed to be complete in a short space of time. | high | meduim | Sean Kaila | Delay the release of the product, allowing for core functionality to be more polished. | Revaluate the requirements against what work is being done to minimuse the riskof spending too much time on unimportant tasks compered to the important ones. | No updates as of 08/05/2021
Risk Assesement